CGU-SIM Briefing

OTC application first, student pathway design second

Prepared for CGU academic and administrative leadership

Open chatbot

Public Q&A assistant for this briefing

# Table of Contents

Click any item below to jump to that section.

Executive Dashboard

Collaboration Architecture

Document Map

Timeline

Workstreams

DMS Modules

Scenario Comparison

Risk Register

Open Questions

Decision Agenda

Source Notes

# Executive Dashboard

## Current project stage

Feasibility, OTC application preparation, and Taiwan admissions-permission assessment. No public launch or final partnership commitment should be assumed.

## Recommended next decision

Authorize a CGU-SIM task force to pursue two linked approval tracks: SIM OTC review and Taiwan MOE permission for an independent admissions model before any public recruitment claim.

## Key indicators

| Metric | Value | Note | Status |
| --- | --- | --- | --- |
| Near-term gate | NDA + Annex review | Annexes 1-3 are released only after NDA signature. | Confirmed by SIM document |
| Regulatory gate | MOE approval | Independent admissions rules must be approved by Taiwan's MOE before implementation. | Confirmed by Taiwan law |
| Initial programme | DMS | DMS has 15 modules, 630 contact hours, and 6/9 module OTC options. | Confirmed by SIM document |
| Staffing floor | 3-5 faculty | Maximum two modules per teacher; 6 modules need at least 3, 9 modules need at least 5. | Confirmed by SIM document |
| Degree posture | Optional CGU return path | The CGU degree depends on credit/time and residency interpretation. | Pending CGU |

## Top five risks

Independent admissions permission may be denied by Taiwan's MOE.

CGU/Taiwan credit or residence requirement may prevent an easy dual-degree story.

Student status during overseas phase may require leave or withdrawal.

NDA no-publicity clause constrains recruitment communications.

Singapore governing law, jurisdiction, and PDPA may require escalation.

## Near-term actions

| Action | Owner | Due | Dependency |
| --- | --- | --- | --- |
| Create task force and name accountable leads | Project sponsor or designee | Initiation phase | Leadership authorization |
| Confirm whether the student model requires independent admissions and MOE approval | Admissions / Academic Affairs | Policy-framing phase | University Act Article 24 and CGU admissions rules |
| Send NDA to legal review and identify signatory authority | Legal / International Affairs | Legal gate phase | NDA template and CGU delegation rules |
| Ask Academic Affairs to rule on credits, residence, student status, and 16+2 handling | Academic Affairs | Academic rules phase | June 9 conversation facts and DMS contact-hour data |
| Inventory English-medium faculty for the first 6 and 9 DMS-module scenarios | Academic lead / Staffing lead | Application-preparation phase | Teaching profile forms, CVs, certificates, transcripts |
| Prepare SIM clarification list for post-NDA Annex review | SIM liaison | SIM clarification phase | Legal clearance to receive Annexes |

# Collaboration Architecture

CGU should treat the OTC application and Taiwan admissions permission as parallel foundations. The student pathway and optional CGU degree design should be built only after CGU confirms credit, status, legal, staffing, and MOE conditions.

## Foundation layer: SIM Overseas Teaching Centre

CGU applies to deliver approved SIM diploma modules in Taiwan under SIM quality standards.

### Confirmed

OTC application form is required

SIM reviews application and may conduct onsite audit

Formal agreement is due within 180 days after SIM approval

### Unresolved

Exact Annex 1-3 operating terms

Fees and revenue share

Minimum cohort size for post-cohort accreditation

## Strategic pathway layer: admissions and progression

CGU may recruit students through an independent admissions model, combine CGU registration with SIM offer, and design progression to SIM Singapore and partner universities.

### Confirmed

June 9 conversation supports use of CGU admissions and SIM additional offer

Students initially register at CGU

Parallel recruitment outside regular 學測/分科 paths likely requires a distinct admissions rule

### Unresolved

MOE permission for independent admissions

Student status during Singapore phase

Credit/time rule for CGU degree

Public recruitment wording before SIM and MOE permission

## Regulatory layer: Taiwan admissions approval

Because students would be recruited in parallel with regular routes and pay a different tuition model, CGU must treat independent admissions approval as a go/no-go condition.

### Confirmed

University Act Article 24 requires university admissions rules to be submitted to MOE for approval before implementation

A rejected MOE application would stop the student-recruitment collaboration even if SIM review proceeds

### Unresolved

Whether CGU should apply through a special project, programme-specific admissions rule, or another approved mechanism

How tuition, quota, student status, and SIM progression should be represented in the MOE submission

# Document Map

| Document | Role | Action | Owner | Dependency |
| --- | --- | --- | --- | --- |
| Diploma_Business OTC Application Guide_11Sep2025.docx | OTC process authority | Translate process into CGU gate plan and request Annexes after NDA. | SIM liaison | NDA signature for Annexes |
| Application Form_10Nov25.docx | Formal OTC application | Build evidence pack across OTC identity, delivery plan, staffing, facilities, recruitment, and projections. | Operations lead | Signatory proof, programme scope, staffing inventory |
| Taiwan University Act, Article 24 | Admissions approval authority | Confirm MOE approval route for independent admissions, tuition distinction, quota treatment, and student-status disclosure. | Admissions / Academic Affairs | CGU admissions design and MOE interpretation |
| Course info_Diploma in Management Studies.pdf | DMS course facts | Use module list, 15-month duration, and contact-hour facts for mapping. | Academic lead | SIM confirmation of final 6/9 module order |
| Academic Staff Teaching Profile Form- 10162025.xlsx | Faculty approval evidence | Collect profile forms, CVs, certificates, transcripts, English proficiency, and module assignments. | Staffing lead | Faculty nominations |
| NDA template | Legal gate | Review Singapore law, PDPA, no-publicity clause, seven-year confidentiality, and signatory details. | Legal lead | Approved signatory |
| Prior AI drafts | Reference synthesis only | Use for storyline comparison; do not treat as evidence without source cross-check. | Project lead | June 9 conversation, SIM documents, and law sources |

# Timeline

| Phase | Window | Owner | Deliverable | Gate |
| --- | --- | --- | --- | --- |
| Phase 0: Internal alignment | Initiation phase | Project sponsor / project lead | Task force charter, scope, owners, and decision log | Leadership authorizes feasibility/application phase |
| Phase 1: Legal and policy framing | Before external commitments | Legal / Academic Affairs / Admissions | NDA review path, MOE admissions-permission route, and public-claims boundary | CGU agrees this is a dual-gate project |
| Phase 2: SIM clarification and MOE admissions design | After initial authorization | SIM liaison / Admissions lead | SIM clarification memo plus independent-admissions concept for MOE consultation | Critical SIM and MOE feasibility questions are answerable |
| Phase 3: Evidence pack and staffing build | Application-preparation phase | Operations / Staffing / Academic lead | OTC evidence pack, staffing forms, academic mapping, admissions rationale | Internal quality review before either submission |
| Phase 4: Parallel external review | Authority-paced | SIM liaison / Admissions lead | SIM review, audit preparation, teaching-site evidence, MOE admissions submission and clarifications | Both SIM and MOE approvals are obtained or remediation is defined |
| Phase 5: Formal agreement and launch permission | After both approvals | Legal / signatory / Admissions | Agreement signed by required parties and approved recruitment/advising terms | No implementation before SIM approval and MOE permission |
| Phase 6: Pre-launch operations | Approved launch window | Recruitment and operations leads | Approved advising scripts, timetable, class/exam operations | No-publicity, academic, and admissions approvals cleared |
| Phase 7: First cohort and review | Post-launch | Academic head / admin staff | Delivery documentation, post-cohort accreditation, annual review | SIM accreditation and annual progress review |

# Workstreams

| Workstream | Owner | Deliverable | Decision rights | Deadline |
| --- | --- | --- | --- | --- |
| Executive sponsorship | Project sponsor or designated lead | Charter, mandate, escalation route | Scope and resource authorization | Initiation phase |
| Academic mapping | College / department academic lead | DMS module mapping, 6/9-module recommendation, faculty assignments | Academic fit and course equivalence proposal | Academic-mapping phase |
| Academic Affairs | Academic Affairs lead | Credit conversion, recognition, CGU degree eligibility, student status | CGU policy interpretation and approval pathway | Academic-rules phase |
| Admissions / MOE compliance | Admissions and Academic Affairs leads | Independent-admissions rationale, tuition/quota framing, MOE consultation and submission path | Whether the recruitment model can lawfully proceed | Policy-framing phase |
| Legal | Legal lead | NDA review, PDPA controls, no-publicity guidance, agreement red flags | Contract risk and signature readiness | Legal gate phase |
| International liaison | International Affairs / SIM liaison | SIM questions, document exchange, meeting records | External coordination discipline | SIM clarification phase |
| Staffing | Staffing lead | Teaching profile forms, CVs, certificates/transcripts, English-readiness matrix | Faculty readiness for 6/9 module scenarios | Staffing-readiness phase |
| Operations | Operations lead | Facilities evidence, timetable, assessment logistics, audit file | Operational feasibility and launch readiness | Application-preparation phase |
| Recruitment and advising | Recruitment/advising lead | Independent admissions concept, family advising scripts, no-publicity compliance | Student-facing claims after SIM and MOE approvals | After approval route is confirmed |
| Finance | Finance/business-case lead | Fee model, revenue share analysis, audit costs, break-even threshold | Business sustainability recommendation | After Annexes |

# DMS Modules

The official DMS PDF lists 15 modules at 42 contact hours each, totaling 630 contact hours over a 15-month full-time programme.

The DMS PDF order differs from the xlsx Data-sheet DMS list. CGU should not lock a teaching sequence until SIM confirms the exact 6 or 9 modules.

| SIM module | Hours | Possible CGU equivalent | Potential CGU faculty | English-medium readiness | Qualification evidence | Risk |
| --- | --- | --- | --- | --- | --- | --- |
| English For Business | 42 | Business English / professional communication | Language or management faculty | High required | CV, degree certificate, transcript, English proficiency | Medium |
| Business Communications | 42 | Business communication | Management / language faculty | High required | Profile form and teaching experience | Medium |
| Business Mathematics | 42 | Business mathematics | Management / quantitative methods | Medium-high | Qualification and transcript | Medium |
| Microeconomics | 42 | Economics | Economics / management faculty | Medium-high | Relevant academic qualification | Medium |
| Business Statistics | 42 | Statistics / data analysis | IM / management analytics faculty | Medium-high | Quantitative teaching evidence | Low-medium |
| Information Systems for Business | 42 | Information systems | Information Management | Medium-high | IS qualification and English teaching readiness | Low |
| Financial Accounting | 42 | Accounting | Accounting faculty | Medium-high | Accounting qualification and teaching profile | Medium-high |
| Managerial Accounting | 42 | Managerial accounting | Accounting faculty | Medium-high | Qualification plus module match | Medium-high |
| Business Finance | 42 | Finance | Finance faculty | Medium-high | Finance qualification and transcript | Medium-high |

# Scenario Comparison

## A. OTC-only pilot

| Student value | CGU value | Approvals | Risk |
| --- | --- | --- | --- |
| SIM modules in Taiwan with lower transition pressure | Tests delivery capability before public pathway claims | NDA, SIM OTC application, internal course approval; MOE needed if used for independent recruitment | Best first implementation posture |

Staffing load: 3+ faculty for 6 modules  |  Credit complexity: Moderate if used for CGU recognition  |  Timeline: Earliest after SIM approval, without public pathway recruitment

## B. OTC + SIM progression after 6 modules

| Student value | CGU value | Approvals | Risk |
| --- | --- | --- | --- |
| Early overseas pathway with Taiwan first stage | Recruitment story without full first-year burden | SIM OTC approval plus MOE-approved independent admissions, advising, and student-status rules | MOE rejection, synchronous schedule, credit posting |

Staffing load: At least 3 faculty  |  Credit complexity: High for CGU retention/credit recovery  |  Timeline: Depends on SIM cycle and MOE approval path

## C. OTC + SIM progression after 9 modules

| Student value | CGU value | Approvals | Risk |
| --- | --- | --- | --- |
| More local preparation before Singapore move | More CGU engagement and more recoverable learning | Same as B, with heavier academic mapping and admissions rationale | Faculty, timetable, and admissions-approval bottlenecks |

Staffing load: At least 5 faculty  |  Credit complexity: High but more mapping value  |  Timeline: Longer local phase; SIM and MOE cycles both matter

## D. Optional CGU degree return path

| Student value | CGU value | Approvals | Risk |
| --- | --- | --- | --- |
| Possible CGU degree plus overseas partner degree | Retention and degree-completion upside | Academic Affairs, college, and MOE-sensitive admissions/tuition review | Do not market as dual degree yet |

Staffing load: Depends on return curriculum  |  Credit complexity: Very high until rule is confirmed  |  Timeline: Second-stage design only

# Risk Register

| Risk | Severity | Likelihood | Owner | Mitigation / Next action |
| --- | --- | --- | --- | --- |
| Independent admissions permission may be denied by Taiwan's MOE. | High | Medium-high | Admissions / Academic Affairs | Treat MOE approval as a parallel go/no-go gate with SIM review; do not recruit until both are cleared. Confirm application route, tuition/quota framing, and submission requirements with MOE. |
| CGU/Taiwan credit or residence requirement may prevent an easy dual-degree story. | High | High | Academic Affairs | Position CGU degree as optional pending formal Academic Affairs interpretation. Issue credit/time/residency ruling. |
| Student status during overseas phase may require leave or withdrawal. | High | High | Academic Affairs | Create advising model and status decision tree before recruitment. Define status options for SIM progression. |
| NDA no-publicity clause constrains recruitment communications. | High | Medium | Legal / recruitment | No public SIM claims until legal and SIM written permission are secured. Draft approved message boundaries. |
| Singapore governing law, jurisdiction, and PDPA may require escalation. | Medium-high | Medium | Legal | Legal review before signature and later agreement negotiation. Complete NDA red-flag memo. |
| Exact blended delivery split is locked behind Annexes and differs from the conversation-stage approximation. | Medium-high | High | SIM liaison | Use Application Form Appendix A as current document fact; reconcile after Annex review. Ask SIM to confirm split by module type. |
| DMS module sequence discrepancy between PDF and xlsx Data sheet. | Medium | High | Academic lead | Do not finalize 6/9-module timetable until SIM confirms sequence. Request official module order. |
| Faculty bottleneck because each teacher is limited to two modules. | High | High | Staffing lead | Run 6-module and 9-module staffing inventory before scope decision. Nominate faculty and collect evidence. |
| Synchronous SIM online schedule may not align with CGU semesters. | High | Medium-high | Operations lead | Build timetable around SIM cycles and avoid assuming local compression. Get SIM timetable flexibility. |
| Exam marking and script-return logistics remain unresolved. | Medium | Medium | Operations lead | Clarify exam paper custody, invigilation, marking, and return chain. Ask SIM for assessment SOP. |
| Fees, revenue share, and audit costs are unavailable until Annexes. | High | High | Finance lead | Delay business-case approval until Annexes are reviewed. Build fee model after Annex release. |
| Minimum cohort size for post-cohort accreditation is unspecified. | Medium | Medium | SIM liaison | Include cohort threshold in SIM clarification log. Ask SIM for threshold and remote verification conditions. |
| Public claims about partner universities may overstate guarantees. | High | Medium | Recruitment / legal | Verify every partner/pathway claim and mark as pending until confirmed. Create claim-review checklist. |

# Open Questions

## CGU Academic Affairs

Is the CGU degree requirement measured by credits, elapsed time, residency, or a combination?

Can SIM contact hours be mapped into CGU credits or micro-courses?

Can SIM modules be embedded into required-course objectives or handled through course exemption?

What student status applies when a student leaves for SIM Singapore?

## Admissions / MOE compliance

Does the different tuition and parallel recruitment model require an independent admissions application?

What MOE approval route is viable for a programme-specific CGU-SIM cohort?

How should quotas, tuition, student status, SIM offer, and overseas progression be disclosed?

What happens to the SIM application work if MOE declines the admissions proposal?

## CGU Legal

Is Singapore governing law and exclusive jurisdiction acceptable?

Who can sign the NDA and later formal agreement?

What internal confidentiality controls are needed?

What no-publicity language is required before recruitment materials are drafted?

## SIM / Jessy

Which DMS module sequence should CGU use?

Which 6 or 9 modules are eligible for CGU delivery?

What is the exact split of SIM vs OTC hours for exam and non-exam modules?

How flexible are synchronous online sessions for a Taiwan cohort?

Who marks exams, and must scripts be returned to Singapore?

What are the fee and revenue-share terms?

What is the minimum cohort size for accreditation?

What written permission is needed for recruitment materials?

## College leadership

Is DMS the initial target, or should DAC, DBF, DIB, DIT, or GDBA be considered later?

Which departments can provide qualified English-medium faculty?

What level of recruitment and retention tradeoff is acceptable?

# Decision Agenda

## Approve now

Create the CGU-SIM task force.

Proceed with legal review of the NDA.

Assign authorized signatory owner and proof-of-authority owner.

Authorize Academic Affairs consultation on credit, status, and recognition.

Authorize admissions/MOE compliance assessment for independent recruitment.

Authorize staffing inventory for 6-module and 9-module DMS scenarios.

## Defer

Public launch language.

Dual-degree or CGU-degree marketing claim.

Final 6/9-module commitment.

Business model approval before Annex fees and terms are known.

Student recruitment until SIM and MOE approvals are both cleared.

## Verify through task force

Exact DMS module order and eligible OTC modules.

MOE approval route for independent admissions, tuition, and quota treatment.

Exam marking, script custody, and assessment SOP.

Scheduling flexibility for SIM synchronous components.

Minimum cohort size and accreditation mode.

Permission required for recruitment materials.

# Source Notes

| Claim | Source | Status | Briefing implication |
| --- | --- | --- | --- |
| Students may enter through CGU admissions, register at CGU, and receive an additional SIM offer. | June 9, 2026 CGU-SIM conversation | Confirmed by June 9 conversation | Design advising and status rules before recruitment. |
| University admissions rules, including single-school admissions, must be drafted by the university and submitted to Taiwan's MOE for approval before implementation. | Taiwan University Act, Article 24 | Confirmed by Taiwan law | A CGU-SIM independent admissions model is a parallel approval track, not an internal scheduling detail. |
| CGU degree requires at least half of required credits/time at CGU/Taiwan; exact rule needs confirmation. | June 9, 2026 CGU-SIM conversation | Pending CGU | Do not present the collaboration as a confirmed dual-degree model. |
| DMS has 15 modules, 42 contact hours each, totaling 630 hours. | Course info_Diploma in Management Studies.pdf | Confirmed by SIM document | Use DMS as first academic mapping target. |
| SIM OTC approval involves application review, onsite audit, teaching staff review, final decision, agreement within 180 days, post-cohort accreditation, and annual review. | Diploma_Business OTC Application Guide_11Sep2025.docx | Confirmed by SIM document | Sequence the project as a multi-gate application. |
| The Application Form includes DMS 6-module and 9-module options and Appendix A blended delivery hours. | Application Form_10Nov25.docx | Confirmed by SIM document | Compare 6-module and 9-module scenarios before scope decision. |
| Teaching profile workbook limits each teacher to two modules and requires certificates/transcripts. | Academic Staff Teaching Profile Form- 10162025.xlsx | Confirmed by SIM document | Faculty evidence is a critical bottleneck. |
| NDA imposes no-publicity, PDPA, Singapore law, and seven-year confidentiality obligations. | NDA template | Confirmed by SIM document | Legal review and internal confidentiality controls are immediate gates. |
| If either SIM OTC approval or Taiwan MOE admissions permission fails, the student-recruitment collaboration cannot proceed as designed. | Synthesis of SIM OTC Guide and Taiwan University Act Article 24 | Confirmed by Taiwan law | Manage the work as intertwined dual applications with a shared launch decision. |